## Slide 1: marcive UPDATE for USG Federal Depository libraries
June 15, 2017

## Slide 2: MARCIVE implementation timeline
Early March – last full record load from MARCIVE
March 30th – last day to add records to Voyager
April 21st – last day to update records in Voyager
April 24th – May 25th – Voyager frozen
May 1st – institutions that currently use MARCIVE need to cancel their subscriptions
May 26th – Alma goes live
  No copy cataloging for new federal documents
June – Test load of MARCIVE records into Alma
  Workflows tested and documented
July – MARCIVE record loads for all USG FDLs begin
  Training for USG FDLs
  Processing for new federal documents begins

## Slide 3: Done as of May 31st
Decide who needs to be on the USG FDL MARCIVE listserv
  Depository coordinators plus tech services staff
Check/update selection profiles with GPO
Check with MARCIVE about canceling current subscriptions
Plan for how to handle shipments from the end of March until early July
  Will need to check all shipments against shipping lists and claim as necessary
Decide if your institution wants to use any of the following:
  MARCIVE Shipping List Service
  Smart barcodes from MARCIVE

## Slide 5: How it works: electronic items
Bib records loaded in the NZ monthly
Records for ALL electronic items appear in Primo for ALL USG libraries, not just FDLs
  Works like GALILEO purchased e-books
  FDLs will not have to touch records, but...
  Will not have the option to suppress records in IZ
Updates to bib records done via OCLC WorldShare
Bib record in Alma NZ
Record in Primo

## Slide 6: How it should work: Tangible items
Alma
Holdings information based on each FDLs’ selection profile attached to a single bib record
Bib records loaded in the NZ monthly
Records appear in the IZ based on holdings record
FDL processes tangible documents once record is loaded
Updates to bib records done via OCLC WorldShare
Bib record
UGA hldgs
GIT
hldgs
GSoU hldgs
GCSU hldgs
GSU
hldgs
= NZ
= IZ

## Slide 7: Next steps
First test record load expected by next week
  MARCIVE GPO Import Project group will evaluate and make adjustments as necessary
By July
  Training and documentation for USG FDLs
  Records go live in Alma
  Processing for new tangible federal documents begins
After July
  Will continue to evaluate record loads, especially records for electronic items

## Slide 8: Further information
G3 Alma & Primo Training – FDL MARCIVE
sites.google.com/view/g3almatraining/cataloging/fdl-marcive
Under Cataloging
USGFDL-L@listserv.uga.edu
Listserv for Federal Depository Libraries in the USG
Announcements, questions, etc.

## Slide 9: Questions?